## overview
Project Name | Partcipant Finder
Description | Web app to allow researchers to recruit participants for their experiment
GitHub Repo | https://github.com/pfremp/masters_proj.git
Author | patrickfrempong@gmail.com
Main Funtionality
User Type | Feature Name | Status
All Users | Create an account
View experiments
Edit Account Profile
Participant | Sign-up to experiment
Signup to experiment stand-by
Sort Experiments
View Matched Experiments
View Diary of Experiments
Share Experiment
View Experiment History
Researcher | Post Experiment
Create Researcher Profile
Cancel Experiment
Invite Participant
Process Applications
Search Participant Pool

## To Do
Name | Description | Priority | Notes | STATUS
Draw ERD |  |  |  | Done
Update ERD
Pop Script
Dissertation
Design Decisions
SpecificationList
Testing
Setup env

## sprint 1
Card No. | Name | Description | Priority | Status | Related (No) | Difficulty / Points | Type | Notes | Testing | Documents | MTV
1 | Participant Model | •Participant Model - remove address, postcode, •Student Bool should be an option within the occupation list •Keep city and country option (use django countries plugin) •Gather different levels of education •Gender - add other options (i.e. prefer not to say) •Remove Ethnicity and Religion •Add DOB •Add Languages (can this be a tab?) | Must | In progress |  | 1 | Functionality
2 | Researcher Model | •Add fields URL, Dept, School •Remove DOB | Must | In progress |  | 1 | Functionality
3 | Experiment Model | •Combine long desc with short desc and grab first from ?? •Add url to Exp •Add Voucher to payment type •Remove date •Required Language | Must | Not Started | 4 |  | Functionality | •Design decision: Create new model to handle payment types • The app is just there to initiate the transaction between the researcher and the participant. Date info. Etc is handdle outwitht he app. There may be scope at a later date to add this into the app.
4 | Payment Type | •Create model to handle payment types - Payment types: One off, hourly, Voucher, Free, Other…, Currency | Must | Not Started | 3
5 | Experiment Requirements | •Find 20 experiments from around the uni and make sure the app can handle their requirements. | Should | Not Started |  | 1 | Requirements Gathering
6 | Application Model | •Application model should contain slots that the reserchers can send to the participoants to choose from. •Document the applcation process | Must | Not Started |  | 3 | Functionality
7 | User Personas | •Create user personas for 2 Prof, 1 Student, 1 non-student | Must | Not Started |  | 1 | Requirements Gathering
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34 | [11 empty] | •User signs up as a Participant or Researcher •User received email confirmation •User is redirected to complete profile
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
51
52
53
54