## overview
Project Name | Partcipant Finder
Description | Web app to allow researchers to recruit participants for their experiment
GitHub Repo | https://github.com/pfremp/masters_proj.git
Author | patrickfrempong@gmail.com
Main Funtionality
User Type | Feature Name | Status
All Users | Create an account | Completed
View experiments
Edit Account Profile
Participant | Sign-up to experiment
Signup to experiment stand-by
Sort Experiments
View Matched Experiments
View Diary of Experiments
Share Experiment
View Experiment History
Researcher | Post Experiment
Create Researcher Profile
Cancel Experiment
Invite Participant
Process Applications
Search Participant Pool

## To Do
Name | Description | Priority | Notes | STATUS
Draw ERD |  |  |  | Done
Update ERD
Pop Script
Dissertation
Design Decisions
SpecificationList
Testing
Setup env
Update Dropbox folder

## sprint 1
Card No. | Name | Description | Priority | Status | Related (No) | Difficulty / Points | Type | Notes | Testing | Documents | MTV
1 | Participant Model | •Participant Model - remove address, postcode, •Student Bool should be an option within the occupation list •Keep city and country option (use django countries plugin) •Gather different levels of education •Gender - add other options (i.e. prefer not to say) •Remove Ethnicity and Religion •Add DOB •Add Languages (can this be a tab?) | Must | Completed |  | 1 | Functionality | •Design decision: keep student boolean as u may have students who are part time or students who do work as well as study? •18/7/15 12:24 - Installing Django Cities Light, Receiving some errors so need to install django south 19/7/15: Trying to install django countries light and django-autocomplete-light. Problem with my setup, packages are installing globally and not just within the virtualenv Upgraded to Django V 1.8: - had to install formtools as it is not shipped with django anymore Design Decision: Make scope of project - UK (Expand later) 20/7/15 had to add novalidate to participant form auto complete works, however still having problems with filters was able to add auto complete languages, but will need delimiter as all is displayes in one string 22/7/15 Changed the experiment model to have time slots at a foreign key, timeslot is made up of a date, start time end time and no. of participants. Problems: -datetimefield widget not working in additional formset fields. -dependency between related fields, i.e. country and city -not needing student bool field
2 | Researcher Model | •Add fields URL, Dept, School •Remove DOB | Must | Completed |  | 1 | Functionality
3 | Experiment Model | •Combine long desc with short desc and grab first from ?? •Add url to Exp •Add Voucher to payment type •Remove date •Required Language | Must | Not Started | 4 |  | Functionality | •Design decision: Create new model to handle payment types • The app is just there to initiate the transaction between the researcher and the participant. Date info. Etc is handdle outwitht he app. There may be scope at a later date to add this into the app.
4 | Payment Type | •Create model to handle payment types - Payment types: One off, hourly, Voucher, Free, Other…, Currency | Must | Not Started | 3 |  |  | 22/7/15 payment info was split into another class, dependent form setup - Need to setup auto complete for city field
5 | Experiment Requirements | •Find 20 experiments from around the uni and make sure the app can handle their requirements. | Should | Not Started |  | 1 | Requirements Gathering
6 | Application Model | •Application model should contain slots that the reserchers can send to the participoants to choose from. •Document the applcation process | Must | Not Started |  | 3 | Functionality | 28/7/15 - Got initial application form working --Need to make it more robust: only allow logged in particiapnts to apply - Done ensure that terms have been accepted introducce pre screeen feature don’t allow to apply for same experiment more than once - check that slot isnt full increase counters (timeslot counter, experiment counter) - Current parts counter should only happen once app has been accepted i.e. status is confirmed.
7 | User Personas | •Create user personas for 2 Prof, 1 Student, 1 non-student | Must | Not Started |  | 1 | Requirements Gathering
8 | Population Script | •create population script for latest models | Must | Completed |  | 2 | Functionality | •Created population script. Difficulty of assigning timeslot and payment modules
9 | ERD Diagram | Update Erd | Must | Completed |  | 1 | Requirements Gathering | •Created ERD V3.1
10 | document functionality in cards
11 | note bugs
12 | Application Model
13 | fix other pages
14 | Deploy, Python Anywhere | •Deploy site to python anywhere username: pfremp password: a---4 | Must | In Progress |  | 4 | Functionality | deployed on python anywhere Had some issues with static files had to 'collectstaticfiles' also had to set link for 'PROJECT_ROOT' should make these changes on the localhost version getting keyError with django autocomplete
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
51
52
53
54

## Bugs
No. | Bug Name | Description
1