## Current Functionality
Name of function | related view | Priority | Notes | STATUS
Homepage displaying latest experiments
Registration Form for researcher
Regitration for particiapnt
Researcher can view list of their active experiments:
Researcher has a counter showing how many experiments they have
Participant can view list of their active experiments
participant has counter for 'pending' and 'confirmed' applications
researcher can view experiment history
particiapnt can view experiment history
each experiment has a counter showing how many participants they have
researchers can process applications by updating the status to accept or reject particiapnts
if the experiment is full participants wont be able to apply
page displaying all experiments
single page view for experiment -Paricipant can share experiment externally -Participant can view location of experiment on map -Particiapnt can apply for experiment -Participant can view payment details
Researcher can add experiment -experiment can have multiple timeslots
particiapnt can update their details
researcher can update their details
researcher can delete experiment
participant can withdraw application to experiment
researcher can end experiment
researcher can reactivate an experiment
researcher has a profile page that particiapnts can view
allow researcher to edit experiment
fix problems with languages not saving | fixed
fix problem with timeslot: -not displaying properly -not saving properly | works now
fix google login, make sure users are properly redirected -create function that can be used to check user type at all times.
make sure pages are properly restricted for particular users
setup email functionality for allauth
setup matching feature -par CAN FILTER EXPERIMENTS TO MATCH THEIR PRE -researcher can only display exp to pre match
url design
template names
refactoring
all auth page stylings
hide applied for experiments or show as applied
Google login, no user profile
experiment wishlist
only allow edu domains to signup
show if an experiment has been edited
what happends if I manually sign up with google but when I return I want to use the google login ?
how can a user close their account?
what has to be populated for this to work properly?
Form validation, show units
update user when exp has been changed
link username to profile
calendar, manage experiments
exclude english from language searches
404 page
Change coounters from none out to 10 to 0 out of 10
make all researcher usernames lowercase
prevent old dates
prevent timeslots that don’t match the length
populate more languages
additional info for experiment
httl web url in form
exp form payment explained
check languages for student
experiment name label to experiment name
exp - add timeslot - change label from "add another item"
mark exp as ended
testing errors as opposed to assertions

## overview
Project Name | Partcipant Finder
Description | Web app to allow researchers to recruit participants for their experiment
GitHub Repo | https://github.com/pfremp/masters_proj.git
Author | patrickfrempong@gmail.com
Main Funtionality
User Type | Feature Name | Status
All Users | Create an account | Completed
View experiments
Edit Account Profile
Participant | Sign-up to experiment
Signup to experiment stand-by
Sort Experiments
View Matched Experiments
View Diary of Experiments
Share Experiment
View Experiment History
Researcher | Post Experiment
Create Researcher Profile
Cancel Experiment
Invite Participant
Process Applications
Search Participant Pool

## To Do
Name | Description | Priority | Notes | STATUS
Draw ERD |  |  |  | Done
Update ERD
Pop Script
Dissertation
Design Decisions
SpecificationList
Testing
Setup env
Update Dropbox folder

## sprint 1
Card No. | Name | Description | Priority | Status | Related (No) | Difficulty / Points | Type | Notes | Testing | Documents | MTV
1 | Participant Model | •Participant Model - remove address, postcode, •Student Bool should be an option within the occupation list •Keep city and country option (use django countries plugin) •Gather different levels of education •Gender - add other options (i.e. prefer not to say) •Remove Ethnicity and Religion •Add DOB •Add Languages (can this be a tab?) | Must | Completed |  | 1 | Functionality | •Design decision: keep student boolean as u may have students who are part time or students who do work as well as study? •18/7/15 12:24 - Installing Django Cities Light, Receiving some errors so need to install django south 19/7/15: Trying to install django countries light and django-autocomplete-light. Problem with my setup, packages are installing globally and not just within the virtualenv Upgraded to Django V 1.8: - had to install formtools as it is not shipped with django anymore Design Decision: Make scope of project - UK (Expand later) 20/7/15 had to add novalidate to participant form auto complete works, however still having problems with filters was able to add auto complete languages, but will need delimiter as all is displayes in one string 22/7/15 Changed the experiment model to have time slots at a foreign key, timeslot is made up of a date, start time end time and no. of participants. Problems: -datetimefield widget not working in additional formset fields. -dependency between related fields, i.e. country and city -not needing student bool field
2 | Researcher Model | •Add fields URL, Dept, School •Remove DOB | Must | Completed |  | 1 | Functionality
3 | Experiment Model | •Combine long desc with short desc and grab first from ?? •Add url to Exp •Add Voucher to payment type •Remove date •Required Language | Must | Not Started | 4 |  | Functionality | •Design decision: Create new model to handle payment types • The app is just there to initiate the transaction between the researcher and the participant. Date info. Etc is handdle outwitht he app. There may be scope at a later date to add this into the app.
4 | Payment Type | •Create model to handle payment types - Payment types: One off, hourly, Voucher, Free, Other…, Currency | Must | Not Started | 3 |  |  | 22/7/15 payment info was split into another class, dependent form setup - Need to setup auto complete for city field
5 | Experiment Requirements | •Find 20 experiments from around the uni and make sure the app can handle their requirements. | Should | Not Started |  | 1 | Requirements Gathering
6 | Application Model | •Application model should contain slots that the reserchers can send to the participoants to choose from. •Document the applcation process | Must | Not Started |  | 3 | Functionality | 28/7/15 - Got initial application form working --Need to make it more robust: only allow logged in particiapnts to apply - Done ensure that terms have been accepted introducce pre screeen feature don’t allow to apply for same experiment more than once - check that slot isnt full increase counters (timeslot counter, experiment counter) - Current parts counter should only happen once app has been accepted i.e. status is confirmed.
7 | User Personas | •Create user personas for 2 Prof, 1 Student, 1 non-student | Must | Not Started |  | 1 | Requirements Gathering
8 | Population Script | •create population script for latest models | Must | Completed |  | 2 | Functionality | •Created population script. Difficulty of assigning timeslot and payment modules
9 | ERD Diagram | Update Erd | Must | Completed |  | 1 | Requirements Gathering | •Created ERD V3.1
10 | document functionality in cards
11 | note bugs
12 | Application Model
13 | fix other pages
14 | Deploy, Python Anywhere | •Deploy site to python anywhere username: pfremp password: a---4 | Must | In Progress |  | 4 | Functionality | deployed on python anywhere Had some issues with static files had to 'collectstaticfiles' also had to set link for 'PROJECT_ROOT' should make these changes on the localhost version getting keyError with django autocomplete OR CITIES_LIGHT- Problem seems to be to do with the pythonanywhere hosting package. Since upgrading, things seem to be working properly now.
15 | Experiment Time Slot | BUG |  |  |  |  | Functionality | 30/9/15 •Timeslot not clearing when clicking 'addnew' - time not showing on experiment page, showing up as null
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
51
52
53
54

## Bugs
No. | Bug Name | Description
1

## universities
Institution
Aberystwyth University | 'Aberystwyth University',
Anglia Ruskin University | 'Anglia Ruskin University',
Arts University Bournemouth | 'Arts University Bournemouth',
Aston University | 'Aston University',
Bangor University | 'Bangor University',
Bath Spa University | 'Bath Spa University',
Birkbeck College | 'Birkbeck College',
Birmingham City University | 'Birmingham City University',
Birmingham Conservatoire | 'Birmingham Conservatoire',
Bishop Grosseteste University | 'Bishop Grosseteste University',
Bournemouth University | 'Bournemouth University',
BPP University | 'BPP University',
Brunel University | 'Brunel University',
Buckinghamshire New University | 'Buckinghamshire New University',
Canterbury Christ Church University | 'Canterbury Christ Church University',
Cardiff Metropolitan University | 'Cardiff Metropolitan University',
Cardiff University | 'Cardiff University',
Central School of Speech and Drama | 'Central School of Speech and Drama',
City University | 'City University',
Conservatoire for Dance and Drama | 'Conservatoire for Dance and Drama',
Courtauld Institute of Art | 'Courtauld Institute of Art',
Coventry University | 'Coventry University',
Cranfield University | 'Cranfield University',
De Montfort University | 'De Montfort University',
Edge Hill University | 'Edge Hill University',
Edinburgh Napier University | 'Edinburgh Napier University',
Falmouth University | 'Falmouth University',
Glasgow Caledonian University | 'Glasgow Caledonian University',
Glasgow School of Art | 'Glasgow School of Art',
Glyndŵr University | 'Glyndŵr University',
Goldsmiths College | 'Goldsmiths College',
Guildhall School of Music and Drama | 'Guildhall School of Music and Drama',
Harper Adams University | 'Harper Adams University',
Heriot-Watt University | 'Heriot-Watt University',
Heythrop College | 'Heythrop College',
Imperial College London | 'Imperial College London',
Institute of Cancer Research | 'Institute of Cancer Research',
Institute of Education | 'Institute of Education',
King's College London | 'King's College London',
Kingston University | 'Kingston University',
Leeds Beckett University | 'Leeds Beckett University',
Leeds College of Art | 'Leeds College of Art',
Leeds Trinity University | 'Leeds Trinity University',
Liverpool Hope University | 'Liverpool Hope University',
Liverpool John Moores University | 'Liverpool John Moores University',
London Business School | 'London Business School',
London Metropolitan University | 'London Metropolitan University',
London School of Economics | 'London School of Economics',
London School of Hygiene and Tropical Medicine | 'London School of Hygiene and Tropical Medicine',
London South Bank University | 'London South Bank University',
Loughborough University | 'Loughborough University',
Manchester Metropolitan University | 'Manchester Metropolitan University',
Middlesex University | 'Middlesex University',
Newman University | 'Newman University',
Northumbria University | 'Northumbria University',
Norwich University of the Arts | 'Norwich University of the Arts',
Nottingham Trent University | 'Nottingham Trent University',
Open University | 'Open University',
Oxford Brookes University | 'Oxford Brookes University',
Queen Margaret University | 'Queen Margaret University',
Queen Mary, University of London | 'Queen Mary, University of London',
Queen's University Belfast | 'Queen's University Belfast',
Ravensbourne | 'Ravensbourne',
Robert Gordon University | 'Robert Gordon University',
Roehampton University | 'Roehampton University',
Rose Bruford College | 'Rose Bruford College',
Royal Academy of Music | 'Royal Academy of Music',
Royal Agricultural University | 'Royal Agricultural University',
Royal College of Art | 'Royal College of Art',
Royal College of Music | 'Royal College of Music',
Royal Conservatoire of Scotland | 'Royal Conservatoire of Scotland',
Royal Holloway, University of London | 'Royal Holloway, University of London',
Royal Northern College of Music | 'Royal Northern College of Music',
Royal Veterinary College | 'Royal Veterinary College',
School of Oriental and African Studies | 'School of Oriental and African Studies',
Sheffield Hallam University | 'Sheffield Hallam University',
Southampton Solent University | 'Southampton Solent University',
SRUC | 'SRUC',
St George's Hospital Medical School | 'St George's Hospital Medical School',
St Mary's University, Twickenham | 'St Mary's University, Twickenham',
Staffordshire University | 'Staffordshire University',
Stranmillis University College | 'Stranmillis University College',
Swansea Metropolitan University | 'Swansea Metropolitan University',
Swansea University | 'Swansea University',
Teesside University | 'Teesside University',
The Liverpool Institute for Performing Arts | 'The Liverpool Institute for Performing Arts',
The University of St Andrews | 'The University of St Andrews',
Trinity Laban Conservatoire of Music and Dance | 'Trinity Laban Conservatoire of Music and Dance',
UCL School of Pharmacy | 'UCL School of Pharmacy',
Ulster University | 'Ulster University',
University Campus Suffolk | 'University Campus Suffolk',
University College Birmingham | 'University College Birmingham',
University College London | 'University College London',
University for the Creative Arts | 'University for the Creative Arts',
University of Aberdeen | 'University of Aberdeen',
University of Abertay Dundee | 'University of Abertay Dundee',
University of Bath | 'University of Bath',
University of Bedfordshire | 'University of Bedfordshire',
University of Birmingham | 'University of Birmingham',
University of Bolton | 'University of Bolton',
University of Bradford | 'University of Bradford',
University of Brighton | 'University of Brighton',
University of Bristol | 'University of Bristol',
University of Buckingham | 'University of Buckingham',
University of Cambridge | 'University of Cambridge',
University of Central Lancashire | 'University of Central Lancashire',
University of Chester | 'University of Chester',
University of Chichester | 'University of Chichester',
University of Cumbria | 'University of Cumbria',
University of Derby | 'University of Derby',
University of Dundee | 'University of Dundee',
University of Durham | 'University of Durham',
University of East Anglia | 'University of East Anglia',
University of East London | 'University of East London',
University of Edinburgh | 'University of Edinburgh',
University of Essex | 'University of Essex',
University of Exeter | 'University of Exeter',
University of Glasgow | 'University of Glasgow',
University of Gloucestershire | 'University of Gloucestershire',
University of Greenwich | 'University of Greenwich',
University of Hertfordshire | 'University of Hertfordshire',
University of Huddersfield | 'University of Huddersfield',
University of Hull | 'University of Hull',
University of Keele | 'University of Keele',
University of Kent | 'University of Kent',
University of Lancaster | 'University of Lancaster',
University of Leeds | 'University of Leeds',
University of Leicester | 'University of Leicester',
University of Lincoln | 'University of Lincoln',
University of Liverpool | 'University of Liverpool',
University of London[a] | 'University of London[a]',
University of Manchester | 'University of Manchester',
University of Newcastle | 'University of Newcastle',
University of Northampton | 'University of Northampton',
University of Nottingham | 'University of Nottingham',
University of Oxford | 'University of Oxford',
University of Plymouth | 'University of Plymouth',
University of Portsmouth | 'University of Portsmouth',
University of Reading | 'University of Reading',
University of Salford | 'University of Salford',
University of Sheffield | 'University of Sheffield',
University of South Wales | 'University of South Wales',
University of Southampton | 'University of Southampton',
University of St Mark and St John | 'University of St Mark and St John',
University of Stirling | 'University of Stirling',
University of Strathclyde | 'University of Strathclyde',
University of Sunderland | 'University of Sunderland',
University of Surrey | 'University of Surrey',
University of Sussex | 'University of Sussex',
University of the Arts London | 'University of the Arts London',
University of the Highlands and Islands | 'University of the Highlands and Islands',
University of the West of England | 'University of the West of England',
University of the West of Scotland | 'University of the West of Scotland',
University of Wales, Trinity Saint David | 'University of Wales, Trinity Saint David',
University of Warwick | 'University of Warwick',
University of West London | 'University of West London',
University of Westminster | 'University of Westminster',
University of Winchester | 'University of Winchester',
University of Wolverhampton | 'University of Wolverhampton',
University of Worcester | 'University of Worcester',
University of York | 'University of York',
Writtle College | 'Writtle College',
York St John University | 'York St John University',

## languages
Akan | 'Akan',
Amharic | 'Amharic',
Arabic | 'Arabic',
Assamese | 'Assamese',
Awadhi | 'Awadhi',
Azerbaijani | 'Azerbaijani',
Balochi | 'Balochi',
Belarusian | 'Belarusian',
Bengali | 'Bengali',
Bhojpuri | 'Bhojpuri',
Burmese | 'Burmese',
Cantonese | 'Cantonese',
Cebuano | 'Cebuano',
Chewa | 'Chewa',
Chhattisgarhi | 'Chhattisgarhi',
Chittagonian | 'Chittagonian',
Czech | 'Czech',
Deccan | 'Deccan',
Dhundhari | 'Dhundhari',
Dutch | 'Dutch',
Fula | 'Fula',
Gan | 'Gan',
Greek | 'Greek',
Gujarati | 'Gujarati',
Haitian Creole | 'Haitian Creole',
Hakka | 'Hakka',
Haryanvi | 'Haryanvi',
Hausa | 'Hausa',
Hiligaynon | 'Hiligaynon',
Hindi | 'Hindi',
Hmong | 'Hmong',
Hungarian | 'Hungarian',
Igbo | 'Igbo',
Ilokano | 'Ilokano',
Italian | 'Italian',
Japanese | 'Japanese',
Javanese | 'Javanese',
Jin | 'Jin',
Kannada | 'Kannada',
Kazakh | 'Kazakh',
Khmer | 'Khmer',
Kinyarwanda | 'Kinyarwanda',
Kirundi | 'Kirundi',
Konkani | 'Konkani',
Korean | 'Korean',
Kurdish | 'Kurdish',
Madurese | 'Madurese',
Magahi | 'Magahi',
Maithili | 'Maithili',
Malagasy | 'Malagasy',
Malay/Indonesian | 'Malay/Indonesian',
Malayalam | 'Malayalam',
Marathi | 'Marathi',
Marwari | 'Marwari',
Min Bei | 'Min Bei',
Min Dong | 'Min Dong',
Min Nan | 'Min Nan',
Mossi | 'Mossi',
Nepali | 'Nepali',
Odia | 'Odia',
Oromo | 'Oromo',
Pashto | 'Pashto',
Persian | 'Persian',
Polish | 'Polish',
Portuguese | 'Portuguese',
Punjabi | 'Punjabi',
Quechua | 'Quechua',
Romanian | 'Romanian',
Russian | 'Russian',
Saraiki | 'Saraiki',
Serbo-Croatian | 'Serbo-Croatian',
Shona | 'Shona',
Sindhi | 'Sindhi',
Sinhalese | 'Sinhalese',
Somali | 'Somali',
Sundanese | 'Sundanese',
Swedish | 'Swedish',
Sylheti | 'Sylheti',
Tagalog | 'Tagalog',
Tamil | 'Tamil',
Telugu | 'Telugu',
Thai | 'Thai',
Turkish | 'Turkish',
Turkmen | 'Turkmen',
Ukrainian | 'Ukrainian',
Urdu | 'Urdu',
Uyghur | 'Uyghur',
Uzbek | 'Uzbek',
Vietnamese | 'Vietnamese',
Wu | 'Wu',
Xhosa | 'Xhosa',
Xiang | 'Xiang',
Yoruba | 'Yoruba',
Zhuang | 'Zhuang',
Zulu | 'Zulu',